## Summary
Project Summary
No. | Project Name | Type | Start Date | End Date | Expected Deadline | Status | Prepared By |  | Remarks
[7 empty] | Designer | Programmer |  | New
1 | Lea Hin Co.(Pte) Ltd | SMEZ B2B | 21/1/2021 | 2021-04-02 | 2021-05-02 | Completed | Jasmy | CH | Product details design changes | Pending | UAT
2 | Legion Consortium Limited | CMS | 2021-05-02 | 23/2/2021 | 28/2/2021 | Completed | Jessie | CH |  | Completed
3 | Nims Pte Ltd | B2B Payment | 25/2/2021 | 19/3/2021 |  | Completed | Jessie | CH
4 | Juz Paint (SEA) Pte Ltd | Eshop lite | 22/3/2021 | 15/4/2021 |  | Completed | Nick | CH | Price Filter, 1 parameter
5 | Seng Long Co (S) Pte Ltd | S&O Lite | 19/4/2021 | 27/4/2021 |  | Completed | Jessie | CH | Product Attribute, Enquiry Attachment
6 | Mon Amie Pte Ltd | b2c Eshop lite | 2021-03-05 | 18/5/2021 |  | Completed | Jasmy | CH | Age Check, 1 Paremeter, Two Prod Cate, Insight
7 | Link-Global Pte Ltd (Gshop) | b2c Eshop lite | 21/5/2021 | 2021-03-06 |  | Completed | Nick | CH | Announcement, 1 Parameter, Product Cate Desc, Promo No Expiry
8 | Anda International Pte Ltd. | b2b smez | 2021-04-06 | 28/6/2021 |  | Completed | shuanghong | CH | Brands Home
9 | Anrawkz | b2c | 28/6/2021 | 13/7/2021 |  | Completed | Jessie | CH | 2 Parameters, Color Size Filter, Category Nav
10 | Aplex Eshop | b2c | 14/7/2021 | 29/7/2021 |  | Completed | shuanghong | CH | No Parameter, Bulk Purchase, International Delivery
11 | Best Value Trading Pte Ltd | b2c Eshop lite | 30/7/2021 | 2021-12-08 |  | Completed | Jasmy | CH | Basic b2c
12 | Gmet International Pte Ltd | b2b smez | 16/8/2021 | 26/8/2021 |  | Completed | Jessie | CH | Basic b2b
13 | Auric Pacific Engineering Pte Ltd | b2b smez | 27/8/2021 | 2021-07-09 |  | Completed | shuanghong | CH | brands
14 | Filtration Solution | b2b smez | 2021-08-09 | 17/9/2021 |  | Completed | Jasmy | CH | Basic b2b
15 | Yeochem (S) Pte Ltd | b2b smez | 20/9/2021 | 30/9/2021 |  | Completed | Nicholas | CH | brand with principal
16 | The Wok People | CMS | 2021-04-10 | 15/10/2021 |  | Completed | Jasmy | CH | pure cms
17 | Mizore | b2c | 18/10/2021 | 2021-01-11 |  | Completed | shuanghong | CH | para1
18 | Aik Soon | b2b smez | 2021-10-11 | 19/11/2021 |  | Completed | Jessie | CH | Basic b2b
19 | Hai’s Pte Ltd. | B2B SMEZ | 30/11/2021 | 17/12/2021 |  | Completed | Nick | CH | Basic b2b, tier 1 cate nav
20 | M&N Flavour Pte Ltd | B2B SMEZ | 20/12/2021 | 2022-10-01 |  | Completed | YZ | CH | multi-cate, no prod desc
21 | FlairIllume | B2B SMEZ | 13/1/2022 | 21/2/2022 |  | Completed | Nick | CH | Basic b2b, projects
22 | Kianlong | B2B SMEZ | 23/2/2022 | 2022-07-03 | 2022-09-03 | Pending | Nick | CH | Basic b2b
23 | Statclean Technology (S) Pte Ltd | B2B SMEZ | 2022-08-03 |  |  | New | Jessie | CH | Basic b2b
24
25
26
27

## 1
Developer: | Chin Hong | Project Name: Lea Hin Co. Pte Ltd |  | Date: | 20/1/2021
No. | Item | Description | Layer | Status | Reference | Remarks | Status | Layer
1 | Import Designer File | Make a copy of file from Fileserver (ProductBackup/Designer/Artwork/2020 or 2021 Site: beta.first2link.com/#ProjectName | General | Completed |  |  | New | Aspx Design
2 | Copy Database and rename | Make a copy of Database Template (_B2BB2C_V4) | General | Completed |  |  | Pending | AspxCs Code
3 | Copy Code and rename | Make a copy of .Net Template from staging (wwwrootV4/ _B2BB2C_V4) | General | Completed |  |  | On Hold | Aspx Control
4 | Add Website | Login to Staging and create a new website: Site Name: Project Physical Path: #CodePath IP Address: #...250 Host Name: #Project.staging.creaworld.sg | General | Completed | http://leahin.staging.creaworld.sg/ |  | Removed | DbTable
5 | Add Virtual Directory | Add CKEditor & CK Editor to the website. (From D/DefaultAssembly/CK2018) Alias: CKEditor, CKFinder | General | Completed |  |  | Change | DbScript
6 | Check App Pool | Check Project Advanced Setting: .NET CLR Version: v4.0 32-Bit: True Idle Time-out: 180minutes | General | Completed |  |  | Completed | BackedProxy
7 | Change Database Setting | 1. System Setting (u_email, u_domain) 2. Site Country (u_domain_name) 3. Menus (i_display_order, b_main_menu, b_show_on_footer, i_country_id) set Primary key of Menu to be the display order | DbTable | Completed |  |  |  | BackedDataset
8 | Update Web Config | 1. Change Initial Catalog DB Name 2. Change Developer Email 3. Update Menu Id to coincide db | WebConfig | Completed |  |  |  | WebConfig
9 | Remove dummy data | 1. Run Delete Script to remove all existing unused data. 2. Insert new category from #project product 3. Update required field based on script | DbTable | Completed |  |  |  | General
10 | Generate Taxonomy | /admin/generatetaxanomy | General | Completed
11 | Deploy Git | Create Repo with new Origin, commit and push to git | General | Completed
12 | Site Master Include | 1. Include all CSS, JS, FavIcon files in staging 2. Replace/ Update Site Master to include all extensions | Aspx Design | Completed
13 | Construct Header, Footer | 1. Update Header Class together with NavBar to be loaded as control. 2. Update Footer to include all the classes, links and copyright datetime. | AspxCs Code | Completed
14 | Programming | Coding for all pages |  | Completed
15 | setup image size, width, thumbnails |  |  | Completed
16 | copy database to 10.11.1.100 |  |  | Completed
17 | copy files to 10.11.1.180 |  |  | Completed
18 | setting dns, a record on 181 |  |  | Completed
19 | setup iis express on 180 and configured app pool |  |  | Completed

## 2
Developer: | Chin Hong | Project Name: Legion Consortium Limited |  | Date: | 2021-05-02
No. | Item | Description | Layer | Status | Reference | Remarks | Status | Layer
1 | Import Designer File | Make a copy of file from Fileserver (ProductBackup/Designer/Artwork/2020 or 2021) ( live site: 10.11.1.166: wwwroot/_beta/#Name) Site: beta.first2link.com/#ProjectName | General | Completed |  |  | New | Aspx Design
2 | Copy Database and rename | Make a copy of Database Template (_B2BB2C_V4) | General | Completed |  |  | Pending | AspxCs Code
3 | Copy Code and rename | Make a copy of .Net Template from staging (wwwrootV4/ _B2BB2C_V4) | General | Completed |  |  | On Hold | Aspx Control
4 | Add Website | Login to Staging and create a new website: Site Name: Project Physical Path: #CodePath IP Address: #...250 Host Name: #Project.staging.creaworld.sg | General | Completed | http://legionconsortium.staging.creaworld.sg/ |  | Removed | DbTable
5 | Add Virtual Directory | Add CKEditor & CK Editor to the website. (From D/DefaultAssembly/CK2018) Alias: CKEditor, CKFinder | General | Completed |  |  | Change | DbScript
6 | Check App Pool | Check Project Advanced Setting: .NET CLR Version: v4.0 32-Bit: True Idle Time-out: 180minutes | General | Completed |  |  | Completed | BackedProxy
7 | Change Database Setting | 1. System Setting (u_email, u_domain) 2. Site Country (u_domain_name) 3. Menus (i_display_order, b_main_menu, b_show_on_footer, i_country_id) set Primary key of Menu to be the display order | DbTable | Completed |  |  |  | BackedDataset
8 | Update Web Config | 1. Change Initial Catalog DB Name 2. Change Developer Email 3. Update Menu Id to coincide db | WebConfig | Completed |  |  |  | WebConfig
9 | Remove dummy data | 1. Run Delete Script to remove all existing unused data. 2. Insert new category from #project product 3. Update required field based on script | DbTable | Completed |  |  |  | General
10 | Generate Taxonomy | /admin/generatetaxonomy.aspx | General | Completed
11 | Deploy Git | Create Repo with new Origin, commit and push to git | General | Completed
12 | Site Master Include | 1. Include all CSS, JS, FavIcon files in staging 2. Replace/ Update Site Master to include all extensions | Aspx Design | Completed
13 | Construct Header, Footer | 1. Update Header Class together with NavBar to be loaded as control. 2. Update Footer to include all the classes, links and copyright datetime. | AspxCs Code | Completed
14 | Programming | Coding for all pages |  | Completed
15 | setup image size, width, thumbnails |  |  | Completed
16 | copy database to 10.11.1.100 |  |  | Completed
17 | copy files to 10.11.1.180 |  |  | Completed
18 | setting dns, a record on 181 |  |  | Completed
19 | setup iis express on 180 and configured app pool |  |  | Completed

## 3
Developer: | Chin Hong | Project Name: Legion Consortium Limited |  | Date:
No. | Item | Description | Layer | Status | Reference | Remarks | Status | Layer
1 | Import Designer File | Make a copy of file from Fileserver (ProductBackup/Designer/Artwork/2020 or 2021) ( live site: 10.11.1.166: wwwroot/_beta/#Name) Site: beta.first2link.com/#ProjectName | General | Completed |  |  | New | Aspx Design
2 | Copy Database and rename | Make a copy of Database Template (_B2BB2C_V4) | General | Completed |  |  | Pending | AspxCs Code
3 | Copy Code and rename | Make a copy of .Net Template from staging (wwwrootV4/ _B2BB2C_V4) | General | Completed |  |  | On Hold | Aspx Control
4 | Add Website | Login to Staging and create a new website: Site Name: Project Physical Path: #CodePath IP Address: #...250 Host Name: #Project.staging.creaworld.sg | General | Completed | http://legionconsortium.staging.creaworld.sg/ |  | Removed | DbTable
5 | Add Virtual Directory | Add CKEditor & CK Editor to the website. (From D/DefaultAssembly/CK2018) Alias: CKEditor, CKFinder | General | Completed |  |  | Change | DbScript
6 | Check App Pool | Check Project Advanced Setting: .NET CLR Version: v4.0 32-Bit: True Idle Time-out: 180minutes | General | Completed |  |  | Completed | BackedProxy
7 | Change Database Setting | 1. System Setting (u_email, u_domain) 2. Site Country (u_domain_name) 3. Menus (i_display_order, b_main_menu, b_show_on_footer, i_country_id) set Primary key of Menu to be the display order | DbTable | Completed |  |  |  | BackedDataset
8 | Update Web Config | 1. Change Initial Catalog DB Name 2. Change Developer Email 3. Update Menu Id to coincide db | WebConfig | Completed |  |  |  | WebConfig
9 | Remove dummy data | 1. Run Delete Script to remove all existing unused data. 2. Insert new category from #project product 3. Update required field based on script | DbTable | Completed |  |  |  | General
10 | Generate Taxonomy | /admin/generatetaxonomy.aspx | General | Completed
11 | Deploy Git | Manage Remote, Create Repo with new Origin, commit and push to git | General | Completed
12 | Site Master Include | 1. Include all CSS, JS, FavIcon files in staging 2. Replace/ Update Site Master to include all extensions | Aspx Design | Completed
13 | Construct Header, Footer | 1. Update Header Class together with NavBar to be loaded as control. 2. Update Footer to include all the classes, links and copyright datetime. | AspxCs Code | Completed
14 | Programming | Coding for all pages |  | Completed
15 | setup image size, width, thumbnails |  |  | Completed
16 | copy database to 10.11.1.100 |  |  | Completed
17 | copy files to 10.11.1.180 |  |  | Completed
18 | setting dns, a record on 181 |  |  | Completed
19 | setup iis express on 180 and configured app pool |  |  | Completed

## 4
Developer: | Chin Hong | Project Name: Juz Paint |  | Date:
No. | Item | Description | Layer | Status | Reference | Remarks
1 | Import Designer File | Make a copy of file from Fileserver (ProductBackup/Designer/Artwork/2020 or 2021) ( live site: 10.11.1.166: wwwroot/_beta/#Name) Site: beta.first2link.com/#ProjectName | General | Completed
2 | Copy Database and rename | Make a copy of Database Template (_B2BB2C_V4) | General | Completed |  |  | Status | Layer
3 | Copy Code and rename | Make a copy of .Net Template from staging (wwwrootV4/ _B2BB2C_V4) | General | Completed |  |  | New | Aspx Design
4 | Add Website | Login to Staging and create a new website: Site Name: Project Physical Path: #CodePath IP Address: #...250 Host Name: #Project.staging.creaworld.sg | General | Completed | http://juzpaint.staging.creaworld.sg/ |  | Pending | AspxCs Code
5 | Add Virtual Directory | Add CKEditor & CK Editor to the website. (From D/DefaultAssembly/CK2018) Alias: CKEditor, CKFinder | General | Completed |  |  | On Hold | Aspx Control
6 | Check App Pool | Check Project Advanced Setting: .NET CLR Version: v4.0 32-Bit: True Idle Time-out: 180minutes | General | Completed |  |  | Removed | DbTable
7 | Change Database Setting | 1. System Setting (u_email, u_domain) 2. Site Country (u_domain_name) 3. Menus (i_display_order, b_main_menu, b_show_on_footer, i_country_id) set Primary key of Menu to be the display order | DbTable | Completed |  |  | Change | DbScript
8 | Update Web Config | 1. Change Initial Catalog DB Name 2. Change Developer Email 3. Update Menu Id to coincide db | WebConfig | Completed |  |  | Completed | BackedProxy
9 | Remove dummy data | 1. Run Delete Script to remove all existing unused data. 2. Insert new category from #project product 3. Update required field based on script | DbTable | Completed |  |  |  | BackedDataset
10 | Generate Taxonomy | /admin/generatetaxonomy.aspx | General | Completed |  |  |  | WebConfig
11 | Deploy Git | Manage Remote, Create Repo with new Origin, commit and push to git | General | Completed
12 | Site Master Include | 1. Include all CSS, JS, FavIcon files in staging 2. Replace/ Update Site Master to include all extensions | Aspx Design | Completed
13 | Construct Header, Footer | 1. Update Header Class together with NavBar to be loaded as control. 2. Update Footer to include all the classes, links and copyright datetime. | AspxCs Code | Completed
14 | Programming | Coding for all pages |  | Completed
15 | setup image size, width, thumbnails |  |  | Completed
16 | copy database to 10.11.1.100 |  |  | Completed
17 | copy files to 10.11.1.180 |  |  | Completed
18 | setting dns, a record on 181 |  |  | Completed
19 | setup iis express on 180 and configured app pool |  |  | Completed
20 |  |  |  | Completed
21 |  |  |  | Completed
22 |  |  |  | Completed
23 |  |  |  | Completed
24 |  |  |  | Completed
25 |  |  |  | Completed
26 |  |  |  | Completed
27 |  |  |  | Completed

## 5
Developer: | Chin Hong | Project Name: Seng Long Co (S) Pte Ltd |  | Date:
No. | Item | Description | Layer | Status | Reference | Remarks
1 | Import Designer File | Make a copy of file from Fileserver (ProductBackup/Designer/Artwork/2020 or 2021) ( live site: 10.11.1.166: wwwroot/_beta/#Name) Site: beta.first2link.com/#ProjectName | General | Completed
2 | Copy Database and rename | Make a copy of Database Template (_B2BB2C_V4) | General | Completed |  |  | Status | Layer
3 | Copy Code and rename | Make a copy of .Net Template from staging (wwwrootV4/ _B2BB2C_V4) | General | Completed |  |  | New | Aspx Design
4 | Add Website | Login to Staging and create a new website: Site Name: Project Physical Path: #CodePath IP Address: #...250 Host Name: #Project.staging.creaworld.sg | General | Completed | http://senglong.staging.creaworld.sg/ |  | Pending | AspxCs Code
5 | Add Virtual Directory | Add CKEditor & CK Editor to the website. (From D/DefaultAssembly/CK2018) Alias: CKEditor, CKFinder | General | Completed |  |  | On Hold | Aspx Control
6 | Check App Pool | Check Project Advanced Setting: .NET CLR Version: v4.0 32-Bit: True Idle Time-out: 180minutes | General | Completed |  |  | Removed | DbTable
7 | Change Database Setting | 1. System Setting (u_email, u_domain) 2. Site Country (u_domain_name) 3. Menus (i_display_order, b_main_menu, b_show_on_footer, i_country_id) set Primary key of Menu to be the display order | DbTable | Completed |  |  | Change | DbScript
8 | Update Web Config | 1. Change Initial Catalog DB Name 2. Change Developer Email 3. Update Menu Id to coincide db | WebConfig | Completed |  |  | Completed | BackedProxy
9 | Remove dummy data | 1. Run Delete Script to remove all existing unused data. 2. Insert new category from #project product 3. Update required field based on script | DbTable | Completed |  |  |  | BackedDataset
10 | Generate Taxonomy | /admin/generatetaxonomy.aspx | General | Completed |  |  |  | WebConfig
11 | Deploy Git | Manage Remote, Create Repo with new Origin, commit and push to git | General | Completed
12 | Site Master Include | 1. Include all CSS, JS, FavIcon files in staging 2. Replace/ Update Site Master to include all extensions | Aspx Design | Completed
13 | Construct Header, Footer | 1. Update Header Class together with NavBar to be loaded as control. 2. Update Footer to include all the classes, links and copyright datetime. | AspxCs Code | Completed
14 | Programming | Coding for all pages |  | Completed
15 | setup image size, width, thumbnails |  |  | Completed
16 | copy database to 10.11.1.100 |  |  | Completed
17 | copy files to 10.11.1.180 |  |  | Completed
18 | setting dns, a record on 181 |  |  | Completed
19 | setup iis express on 180 and configured app pool |  |  | Completed
20 |  |  |  | Completed
21 |  |  |  | Completed
22 |  |  |  | Completed
23 |  |  |  | Completed
24 |  |  |  | Completed
25 |  |  |  | Completed
26 |  |  |  | Completed
27 |  |  |  | Completed

## 6
Developer: | Chin Hong | Project Name: Mon Amie Pte Ltd |  | Date:
No. | Item | Description | Layer | Status | Reference | Remarks
1 | Import Designer File | Make a copy of file from Fileserver (ProductBackup/Designer/Artwork/2020 or 2021) ( live site: 10.11.1.166: wwwroot/_beta/#Name) Site: beta.first2link.com/#ProjectName | General | New
2 | Copy Database and rename | Make a copy of Database Template (_B2BB2C_V4) | General | New |  |  | Status | Layer
3 | Copy Code and rename | Make a copy of .Net Template from staging (wwwrootV4/ _B2BB2C_V4) | General | New |  |  | New | Aspx Design
4 | Add Website | Login to Staging and create a new website: Site Name: Project Physical Path: #CodePath IP Address: #...250 Host Name: #Project.staging.creaworld.sg | General | New | http://monamie.staging.creaworld.sg/ |  | Pending | AspxCs Code
5 | Add Virtual Directory | Add CKEditor & CK Editor to the website. (From D/DefaultAssembly/CK2018) Alias: CKEditor, CKFinder | General | New |  |  | On Hold | Aspx Control
6 | Check App Pool | Check Project Advanced Setting: .NET CLR Version: v4.0 32-Bit: True Idle Time-out: 180minutes | General | New |  |  | Removed | DbTable
7 | Change Database Setting | 1. System Setting (u_email, u_domain) 2. Site Country (u_domain_name) 3. Menus (i_display_order, b_main_menu, b_show_on_footer, i_country_id) set Primary key of Menu to be the display order | DbTable | New |  |  | Change | DbScript
8 | Update Web Config | 1. Change Initial Catalog DB Name 2. Change Developer Email 3. Update Menu Id to coincide db | WebConfig | New |  |  | Completed | BackedProxy
9 | Remove dummy data | 1. Run Delete Script to remove all existing unused data. 2. Insert new category from #project product 3. Update required field based on script | DbTable | New |  |  |  | BackedDataset
10 | Generate Taxonomy | /admin/generatetaxonomy.aspx | General | New |  |  |  | WebConfig
11 | Deploy Git | Manage Remote, Create Repo with new Origin, commit and push to git | General | New
12 | Site Master Include | 1. Include all CSS, JS, FavIcon files in staging 2. Replace/ Update Site Master to include all extensions | Aspx Design | New
13 | Construct Header, Footer | 1. Update Header Class together with NavBar to be loaded as control. 2. Update Footer to include all the classes, links and copyright datetime. | AspxCs Code | New
14 | Programming | Coding for all pages |  | New
15 | setup image size, width, thumbnails |  |  | New
16 | copy database to 10.11.1.100 |  |  | New
17 | copy files to 10.11.1.180 |  |  | New
18 | setting dns, a record on 181 |  |  | New
19 | setup iis express on 180 and configured app pool |  |  | New
20 |  |  |  | New
21 |  |  |  | New
22 |  |  |  | New
23 |  |  |  | New
24 |  |  |  | New
25 |  |  |  | New
26 |  |  |  | New
27 |  |  |  | New

## 7
Developer: | Chin Hong | Project Name: Link-Global Pte Ltd |  | Date:
No. | Item | Description | Layer | Status | Reference | Remarks
1 | Import Designer File | Make a copy of file from Fileserver (ProductBackup/Designer/Artwork/2020 or 2021) ( live site: 10.11.1.166: wwwroot/_beta/#Name) Site: beta.first2link.com/#ProjectName | General | Completed
2 | Copy Database and rename | Make a copy of Database Template (_B2BB2C_V4) | General | Completed |  |  | Status | Layer
3 | Copy Code and rename | Make a copy of .Net Template from staging (wwwrootV4/ _B2BB2C_V4) | General | Completed |  |  | New | Aspx Design
4 | Add Website | Login to Staging and create a new website: Site Name: Project Physical Path: #CodePath IP Address: #...250 Host Name: #Project.staging.creaworld.sg | General | Completed | http://linkglobal.staging.creaworld.sg/ |  | Pending | AspxCs Code
5 | Add Virtual Directory | Add CKEditor & CK Editor to the website. (From D/DefaultAssembly/CK2018) Alias: CKEditor, CKFinder | General | Completed |  |  | On Hold | Aspx Control
6 | Check App Pool | Check Project Advanced Setting: .NET CLR Version: v4.0 32-Bit: True Idle Time-out: 180minutes | General | Completed |  |  | Removed | DbTable
7 | Change Database Setting | 1. System Setting (u_email, u_domain) 2. Site Country (u_domain_name) 3. Menus (i_display_order, b_main_menu, b_show_on_footer, i_country_id) set Primary key of Menu to be the display order | DbTable | Completed |  |  | Change | DbScript
8 | Update Web Config | 1. Change Initial Catalog DB Name 2. Change Developer Email 3. Update Menu Id to coincide db | WebConfig | Completed |  |  | Completed | BackedProxy
9 | Remove dummy data | 1. Run Delete Script to remove all existing unused data. 2. Insert new category from #project product 3. Update required field based on script | DbTable | Completed |  |  |  | BackedDataset
10 | Generate Taxonomy | /admin/generatetaxonomy.aspx | General | Completed |  |  |  | WebConfig
11 | Deploy Git | Manage Remote, Create Repo with new Origin, commit and push to git | General | Completed
12 | Site Master Include | 1. Include all CSS, JS, FavIcon files in staging 2. Replace/ Update Site Master to include all extensions | Aspx Design | Completed
13 | Construct Header, Footer | 1. Update Header Class together with NavBar to be loaded as control. 2. Update Footer to include all the classes, links and copyright datetime. | AspxCs Code | Completed
14 | Programming | Coding for all pages |  | Completed
15 | setup image size, width, thumbnails |  |  | Completed
16 | copy database to 10.11.1.100 |  |  | Completed
17 | copy files to 10.11.1.180 |  |  | Completed
18 | setting dns, a record on 181 |  |  | Completed
19 | setup iis express on 180 and configured app pool |  |  | Completed
20 |  |  |  | Completed
21 |  |  |  | Completed
22 |  |  |  | Completed
23 |  |  |  | Completed
24 |  |  |  | Completed
25 |  |  |  | Completed
26 |  |  |  | Completed
27 |  |  |  | Completed

## 8
Developer: | Chin Hong | Project Name: Anda International Pte Ltd. |  | Date:
No. | Item | Description | Layer | Status | Reference | Remarks
1 | Import Designer File | Make a copy of file from Fileserver (ProductBackup/Designer/Artwork/2020 or 2021) ( live site: 10.11.1.166: wwwroot/_beta/#Name) Site: beta.first2link.com/#ProjectName | General | Completed
2 | Copy Database and rename | Make a copy of Database Template (_B2BB2C_V4) | General | Completed |  |  | Status | Layer
3 | Copy Code and rename | Make a copy of .Net Template from staging (wwwrootV4/ _B2BB2C_V4) | General | Completed |  |  | New | Aspx Design
4 | Add Website | Login to Staging and create a new website: Site Name: Project Physical Path: #CodePath IP Address: #...250 Host Name: #Project.staging.creaworld.sg | General | Completed | http://linkglobal.staging.creaworld.sg/ |  | Pending | AspxCs Code
5 | Add Virtual Directory | Add CKEditor & CK Editor to the website. (From D/DefaultAssembly/CK2018) Alias: CKEditor, CKFinder | General | Completed |  |  | On Hold | Aspx Control
6 | Check App Pool | Check Project Advanced Setting: .NET CLR Version: v4.0 32-Bit: True Idle Time-out: 180minutes | General | Completed |  |  | Removed | DbTable
7 | Change Database Setting | 1. System Setting (u_email, u_domain) 2. Site Country (u_domain_name) 3. Menus (i_display_order, b_main_menu, b_show_on_footer, i_country_id) set Primary key of Menu to be the display order | DbTable | Completed |  |  | Change | DbScript
8 | Update Web Config | 1. Change Initial Catalog DB Name 2. Change Developer Email 3. Update Menu Id to coincide db | WebConfig | Completed |  |  | Completed | BackedProxy
9 | Remove dummy data | 1. Run Delete Script to remove all existing unused data. 2. Insert new category from #project product 3. Update required field based on script | DbTable | Completed |  |  |  | BackedDataset
10 | Generate Taxonomy | /admin/generatetaxonomy.aspx | General | Completed |  |  |  | WebConfig
11 | Deploy Git | Manage Remote, Create Repo with new Origin, commit and push to git | General | Completed
12 | Site Master Include | 1. Include all CSS, JS, FavIcon files in staging 2. Replace/ Update Site Master to include all extensions | Aspx Design | Completed
13 | Construct Header, Footer | 1. Update Header Class together with NavBar to be loaded as control. 2. Update Footer to include all the classes, links and copyright datetime. | AspxCs Code | Completed
14 | Programming | Coding for all pages |  | Completed
15 | setup image size, width, thumbnails |  |  | Completed
16 | copy database to 10.11.1.100 |  |  | Completed
17 | copy files to 10.11.1.180 |  |  | Completed
18 | setting dns, a record on 181 |  |  | Completed
19 | setup iis express on 180 and configured app pool |  |  | Completed
20 |  |  |  | Completed
21 |  |  |  | Completed
22 |  |  |  | Completed
23 |  |  |  | Completed
24 |  |  |  | Completed
25 |  |  |  | Completed
26 |  |  |  | Completed
27 |  |  |  | Completed

## 9
Developer: | Chin Hong | Project Name: Anrawkz |  | Date:
No. | Item | Description | Layer | Status | Reference | Remarks
1 | Import Designer File | Make a copy of file from Fileserver (ProductBackup/Designer/Artwork/2020 or 2021) ( live site: 10.11.1.166: wwwroot/_beta/#Name) Site: beta.first2link.com/#ProjectName | General | New
2 | Copy Database and rename | Make a copy of Database Template (_B2BB2C_V4) | General | New |  |  | Status | Layer
3 | Copy Code and rename | Make a copy of .Net Template from staging (wwwrootV4/ _B2BB2C_V4) | General | New |  |  | New | Aspx Design
4 | Add Website | Login to Staging and create a new website: Site Name: Project Physical Path: #CodePath IP Address: #...250 Host Name: #Project.staging.creaworld.sg | General | New | http:/anrawkz.staging.creaworld.sg/ |  | Pending | AspxCs Code
5 | Add Virtual Directory | Add CKEditor & CK Editor to the website. (From D/DefaultAssembly/CK2018) Alias: CKEditor, CKFinder | General | New |  |  | On Hold | Aspx Control
6 | Check App Pool | Check Project Advanced Setting: .NET CLR Version: v4.0 32-Bit: True Idle Time-out: 180minutes | General | New |  |  | Removed | DbTable
7 | Change Database Setting | 1. System Setting (u_email, u_domain) 2. Site Country (u_domain_name) 3. Menus (i_display_order, b_main_menu, b_show_on_footer, i_country_id) set Primary key of Menu to be the display order | DbTable | New |  |  | Change | DbScript
8 | Update Web Config | 1. Change Initial Catalog DB Name 2. Change Developer Email 3. Update Menu Id to coincide db | WebConfig | New |  |  | Completed | BackedProxy
9 | Remove dummy data | 1. Run Delete Script to remove all existing unused data. 2. Insert new category from #project product 3. Update required field based on script | DbTable | New |  |  |  | BackedDataset
10 | Generate Taxonomy | /admin/generatetaxonomy.aspx | General | New |  |  |  | WebConfig
11 | Deploy Git | Manage Remote, Create Repo with new Origin, commit and push to git | General | New
12 | Site Master Include | 1. Include all CSS, JS, FavIcon files in staging 2. Replace/ Update Site Master to include all extensions | Aspx Design | New
13 | Construct Header, Footer | 1. Update Header Class together with NavBar to be loaded as control. 2. Update Footer to include all the classes, links and copyright datetime. | AspxCs Code | New
14 | Programming | Coding for all pages |  | New
15 | setup image size, width, thumbnails |  |  | New
16 | copy database to 10.11.1.100 |  |  | New
17 | copy files to 10.11.1.180 |  |  | New
18 | setting dns, a record on 181 |  |  | New
19 | setup iis express on 180 and configured app pool |  |  | New
20 |  |  |  | New
21 |  |  |  | New
22 |  |  |  | New
23 |  |  |  | New
24 |  |  |  | New
25 |  |  |  | New
26 |  |  |  | New
27 |  |  |  | New

## Sheet2
Type
Category | Category 1 | Category 1.1 | Category 1.1.1
Product | ProdName | ProdCode | ProdDesc
| Air Cooler | 1
| Blender | 2
| Bread Toaster | 3
Category | Category 2 | Category 2.1
Product | ProdName | ProdCode | ProdDesc
| Chiller | 1
| Cloth Dryer | 2
| Coffee Maker | 3
Category | Category 2 | Category 2.2
Category | Category 3
Category | Category 5 | Category 5.1

## Sheet1
i_menu_id | u_title | i_parent_id | i_display_order | b_main_menu | b_show_on_footer | u_menu_contents | d_created_date | d_last_modified | i_author_id | i_banner_id | i_country_id | u_subpage_title | b_use_sidemenu | d_publish_on | u_customfield_1 | u_customfield_2 | u_customfield_3 | u_customfield_4 | u_external_url | u_meta_desc | u_meta_keyword | u_meta_title
1 | Home | 0 | 1 | 1 | 0 |  | 42830.4153 | 44229.7464 | 3 | -1 | 1 |  | 0 | 2019-07-17 01:00
2 | About Us | 0 | 2 | 1 | 1 |  | 42830.457 | 44229.7881 | 3 | -1 | 1 |  | 0 | 2019-07-18 01:00
3 | Services | 0 | 3 | 1 | 1 |  | 42830.4986 | 44229.8297 | 3 | -1 | 1 |  | 0 | 2019-07-19 01:00
4 | Investor Relations | 0 | 4 | 1 | 1 |  | 42830.5403 | 44229.8714 | 3 | -1 | 1 |  | 0 | 2019-07-20 01:00
5 | Corporate Governance | 0 | 5 | 1 | 1 |  | 42830.582 | 44229.9131 | 3 | -1 | 1 |  | 0 | 2019-07-21 01:00
6 | Contact Us | 0 | 6 | 1 | 1 |  | 42830.6236 | 44229.9547 | 3 | -1 | 1 |  | 0 | 2019-07-22 01:00 |  |  |  | <p>[FORM]</p>
7 | Terms & Conditions | 0 | 7 | 1 | 1 |  | 42830.6653 | 44229.9964 | 3 | -1 | -1 |  | 0 | 2019-07-23 01:00
8 | Documents | 0 | 8 | 1 | 1 |  | 42830.707 | 44230.0381 | 3 | -1 | -1 |  | 0 | 2019-07-24 01:00
9 | Recipes | 0 | 9 | 1 | 1 |  | 42830.7486 | 44230.0797 | 3 | -1 | -1 |  | 0 | 2019-07-25 01:00
10 | FAQ | 0 | 10 | 1 | 1 |  | 42830.7903 | 44230.1214 | 3 | -1 | -1 |  | 0 | 2019-07-26 01:00
11 | Products | 0 | 11 | 1 | 1 |  | 42830.832 | 44230.1631 | 3 | -1 | -1 |  | 0 | 2019-07-27 01:00

## Sheet3
0 | Air Cooler | 3 | 1 | 1 | 0 | 2020-04-20 13:56
0 | Blender | 3 | 1 | 2 | 0 | 2020-04-21 13:56
0 | Bread Toaster | 3 | 1 | 3 | 0 | 2020-04-22 13:56
0 | Cast Iron Gas Stove | 3 | 1 | 4 | 0 | 2020-04-23 13:56
0 | Chiller | 3 | 1 | 5 | 0 | 2020-04-24 13:56
0 | Cloth Dryer | 3 | 1 | 6 | 0 | 2020-04-25 13:56
0 | Coffee Maker | 3 | 1 | 7 | 0 | 2020-04-26 13:56
0 | Deep Fryer | 3 | 1 | 8 | 0 | 2020-04-27 13:56
0 | Drink Chiller | 3 | 1 | 9 | 0 | 2020-04-28 13:56
0 | Electric Air-Pot | 3 | 1 | 10 | 0 | 2020-04-29 13:56
0 | Electric Fan | 3 | 1 | 11 | 0 | 2020-04-30 13:56
0 | Electric Grill | 3 | 1 | 12 | 0 | 2020-05-01 13:56
0 | Electric Hot Plate | 3 | 1 | 13 | 0 | 2020-05-02 13:56
0 | Electric Iron | 3 | 1 | 14 | 0 | 2020-05-03 13:56
0 | Electric Kettle Jug | 3 | 1 | 15 | 0 | 2020-05-04 13:56
0 | Electric Oven | 3 | 1 | 16 | 0 | 2020-05-05 13:56
0 | Electric Rice Cooker | 3 | 1 | 17 | 0 | 2020-05-06 13:56
0 | Electric Wok | 3 | 1 | 18 | 0 | 2020-05-07 13:56
0 | Food Processor / Mixer | 3 | 1 | 19 | 0 | 2020-05-08 13:56
0 | Food Steamer | 3 | 1 | 20 | 0 | 2020-05-09 13:56
0 | Free Standing Gas Cooker | 3 | 1 | 21 | 0 | 2020-05-10 13:56
0 | Freezer | 3 | 1 | 22 | 0 | 2020-05-11 13:56
0 | Garment Steamer | 3 | 1 | 23 | 0 | 2020-05-12 13:56
0 | Gas Burner | 3 | 1 | 24 | 0 | 2020-05-13 13:56
0 | Gas Cooker | 3 | 1 | 25 | 0 | 2020-05-14 13:56
0 | Gas Lantern | 3 | 1 | 26 | 0 | 2020-05-15 13:56
0 | Hair Dryer / Hair Straightener | 3 | 1 | 27 | 0 | 2020-05-16 13:56
0 | Hurricane Lantern | 3 | 1 | 28 | 0 | 2020-05-17 13:56
0 | Induction Cooker | 3 | 1 | 29 | 0 | 2020-05-18 13:56
0 | Infrared Cooker | 3 | 1 | 30 | 0 | 2020-05-19 13:56
0 | Juicer | 3 | 1 | 31 | 0 | 2020-05-20 13:56
0 | Kerosene Pressure Lantern | 3 | 1 | 32 | 0 | 2020-05-21 13:56
0 | Kerosene Stove | 3 | 1 | 33 | 0 | 2020-05-22 13:56
0 | Microwave Oven | 3 | 1 | 34 | 0 | 2020-05-23 13:56
0 | Multi-Cooker | 3 | 1 | 35 | 0 | 2020-05-24 13:56
0 | Non-Electric Appliances | 3 | 1 | 36 | 0 | 2020-05-25 13:56
0 | Pressure Burner | 3 | 1 | 37 | 0 | 2020-05-26 13:56
0 | Pressure Oil Tank | 3 | 1 | 38 | 0 | 2020-05-27 13:56
0 | Pressure Stove | 3 | 1 | 39 | 0 | 2020-05-28 13:56
0 | Refrigerator | 3 | 1 | 40 | 0 | 2020-05-29 13:56
0 | Sandwich Maker | 3 | 1 | 41 | 0 | 2020-05-30 13:56
0 | Slow Cooker | 3 | 1 | 42 | 0 | 2020-05-31 13:56
0 | Solenoid Pump | 3 | 1 | 43 | 0 | 2020-06-01 13:56
0 | Vacuum Cleaner | 3 | 1 | 44 | 0 | 2020-06-02 13:56
0 | Washing Machine | 3 | 1 | 45 | 0 | 2020-06-03 13:56
0 | Water Boiler | 3 | 1 | 46 | 0 | 2020-06-04 13:56
0 | Water Dispenser | 3 | 1 | 47 | 0 | 2020-06-05 13:56
0 | Wine Cooler | 3 | 1 | 48 | 0 | 2020-06-06 13:56